## Slide 1: GreenCircle Certified Database Project
Project Status and Timeline Updates

## Slide 2: Project Timeline Updates
Tasks | Timeline
Week Start Date | 6/23 | 6/30 | 7/7 | 7/14 | 7/21 | 7/28 | 8/4 | 8/11 | 8/18 | 8/25 | 9/1 | 9/8 | 9/15 | 9/22 | 9/29
Week End Date | 6/27 | 7/4 | 7/11 | 7/18 | 7/25 | 8/1 | 8/8 | 8/15 | 8/22 | 8/29 | 9/5 | 9/12 | 9/19 | 9/26 | 10/3
Requirements & Wireframes |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front-end Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Architecture / Environment Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Database Expansion |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
API Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Front-end Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Business Acceptance Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deployment & Configuration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Milestones:
6/27 – Wireframes & Requirement complete
9/5 – Development Complete
9/19 – Testing Complete
10/3 – Go live
Coordination:
9/8 – 9/19 : Business Acceptance Testing, Defect Resolution
9/8 – 9/19 : API Testing with Amazon
9/22 – 10/3 : Deployment Activities

## Slide 3: GreenCircle Certified Database Site Map
Assumptions:
Certificate List 1.0 is a different page than Certificates 3.0.
Admin will have the ability to Add, Edit or Delete a Certificate, Company, Products, Users, Certificate Type, Product Types and Tags.
Notes:
CRUD: [Create, Read, Update, Delete] – Wireframes include the details of the screens.
Notifications & Alerts: Color-coded: Green for success, Red for errors, Yellow for warnings, Blue/gray for info)
Sign-up Registration will be included but hidden and disabled for all users except the admin.
Notes: Comments:
S2:
  See comment on page 46 may need these pages to edit/delete Product Name or Company Name records unless you can find another way
  How do you add a new field. Not represented anywhere.
  Remove (Roles) from site map.
  Is there an API page – or is that all backend?
  7.1.3 – see comments in section
  Are you accounting for non-phase 1 on purpose? No this was missed when updating the documents.
  Grayed Items: Some were intentionally removing.
  3.3 – This would be clients and partners
  There needs to be interface for the Analyst to be able to add and edit new Product (and associate product category/type to it) and Company. Current DB has this happening in the Cert upload interface and separate pages.

## Slide 4: October 3rd Go-live
The adjusted timeline provides:
  Adequate time for comprehensive development of expanded features
  Proper testing cycles for the enhanced functionality
  Quality assurance for the more complex integrations
  Stakeholder alignment on enhanced deliverables
Scope Evolution Highlights:
  Enhanced Security Features - MFA, audit logging, role-based permissions
  Advanced User Experience - Infinite scrolling, improved filtering, mobile considerations
  Complex Data Management - Sophisticated product ID handling, multi-partner associations
  Extended User Types - External partners, varied client access models

## Slide 5: Design Revision Impact on Delivery
Multiple UI design paths were explored throughout the project
Functionality appeared inconsistently across versions (e.g., filters/buttons in some screens but missing in others)
Comments and revisions introduced fragmentation and slowed alignment
Final design direction is now established, but required more time than originally scoped
Incremental requirements were introduced with scope delivered in fragments.
As new features were added mid-cycle, screens often showed inconsistent functionality.
Each revision improved the system but fragmented design artifacts and slowed decisions.
We are now consolidating all approved elements into a single UI reference to avoid rework.
This will improve quality, reduce QA cycles, and streamline final delivery.

## Slide 6: Final Design Consolidation - Scope Locked
Scope Freeze: No new functionality will be added. Existing design elements are being unified into one master reference.
Fragmented Pages: Screens created during iterative revisions are being merged to ensure every approved feature appears consistently.
Quality Focus: Consolidation eliminates hidden gaps, reduces rework, and accelerates the build and QA phases.
Post-Launch Enhancements: Any new ideas identified after consolidation will be scheduled for a future release cycle.

## Slide 7: Managing Scope and Change Control Plan
Purpose: Structure future requests to maintain control over budget and timelines.
Baseline Locked: As of June 30, the consolidated design is the development baseline.
Transparency: All new requests will be assessed and estimated before inclusion.
No Hidden Drift: Unapproved additions will be deferred to a future release phase.
Process includes request intake, impact review, client approval, and timeline update.
Future changes will follow a simple estimate-and-approve process.
Any additions post-June 30 will be reviewed for:
  Timeline impact
  Cost implication
  System stability
This ensures transparency and avoids unintentional delays during final phases.

## Slide 8: Out of Scope Items – Initial Design Phase
The following items are not included in the current scope and will be considered for future phases:
  New Feature Requests Post-Freeze (after June 30): Any new functionality or UX suggestions will be reviewed separately post-launch
  Non-Core Page Redesigns: Pages not directly tied to core certificate workflows (e.g., user management, admin dashboards) are not part of the initial design scope.
  Advanced Reporting & Analytics Modules: Custom reporting or dashboards requiring dynamic visualizations will be addressed in a future release.
  Undocumented Features – Anything not captured in this document or related requirement files is excluded.
  Integration Beyond Amazon Export: Any third-party system integration beyond current export scope will be handled as a separate project.
  Clone Functionality – Selective field cloning for certificate records is not included.
  Notifications & Alerts – Real-time user notifications are not part of this phase.
  Undocumented Features – Anything not captured in this document or related requirement files is excluded
Note: Any additional functionality or enhancements outside this scope will follow the formal change request process and may be included in a post-launch roadmap.

## Slide 9: Scope Creep Analysis & Timeline Impact
In addition, I had a family emergency that reduced my commitment to the project for a few weeks. Even though we have tried to make up time with all of the additional enhancements. The timeline reflects a accurate schedule to ensure quality and fits to the business needs of the system.
Area | Description | Timeline Impact
Client Requirements | User stories and requirements evolved during design. | +8 weeks
Front-End Redesign | Expanded from basic UI to extensive front-end design | +5–6 weeks
Amazon API Integration | Added detailed field mapping and bi-directional calls. | +1–2 weeks
Product & Bulk Upload | Introduced multi-ID types (ASIN, UPC, GTIN, EAN) and import features. | +2–3 weeks
Field Management | Included inline editing and dynamic field creation. | +2 weeks
Role Management | Introduced 4 user roles with granular permissions. | +1–2 weeks
Dashboards | Added 10+ metrics, tracking, and role-based views. | +1–2 weeks
Stakeholder Feedback | Multiple rounds of design revisions required. | +3–4 weeks
Metric | Original | Revised | Increase
Timeline | 14–18 weeks | 34–40 weeks | +20–22 weeks