## Info
Information
Status | Definition | Action Required |  | Status Summary:
Open | Issue identified but no work started | Needs assignment and prioritization
Updates Pending | Issue acknowledged, work in progress or scheduled | Monitor completion, may need follow-up |  | Open: 18
In Progress | Actively being worked on | Track progress and blockers |  | Updates Pending: 15
Resolved | Issue completed and verified | Confirm resolution meets requirements |  | In Progress: 0
Deferred | Out of scope for current phase | Plan for future development |  | Resolved: 0
Deferred: 6 (Out of Scope)
Item # | Question | Stakeholder | Priority
36 | Partners vs Customers access - specific requirements for Amazon CPF clients/certs? | Business | HIGH
37 | Internal tags visibility - can external users see if assigned? Was this a requirement? | Business | MEDIUM
38 | Thousands of ASINs under one cert - how to handle display and navigation? | Business/UX | MEDIUM
39 | Reference Management - what is this navigation item for? | Business | LOW

## Out of Scope
OUT OF SCOPE ITEMS (Documented for future phases)
Item # | Description | Reason | Future Phase | Notification System Design (Future Implementation)
30 | Notifications & Alerts | Not included in initial scope | Phase 2
31 | Clone Feature Enhancements | Selective field carry-over functionality | Phase 2 | Color Coding: Green (success), Red (errors), Yellow (warnings), Blue/Gray (info)
32 | Bulk Upload for Product Identifiers | ASIN, UPC, GTIN, EAN bulk upload via copy/paste or file | Phase 2 | Alert Types: Profile updates, changes saved, session expiration, unsaved changes, validation errors, new versions, export status
33 | Product-Specific Fields | Additional data fields for products associated with ASINs | Phase 2
34 | Customized Reporting Widgets | Dashboard widgets for external users | Phase 2
35 | Third-Party API Integrations | Beyond explicitly defined integrations | Phase 2 | Out of Scope Items (Initial Phase)
Excluded Features
1. Notifications & Alerts - No real-time notifications or system alerts
2. Clone Functionality - Certificate cloning with selective field carry-over
3. Bulk Upload for Product IDs - File upload capabilities for ASIN, UPC, GTIN, EAN
4. Product-Specific Fields - Additional data fields for product identifiers
5. Customized Reporting Widgets - Dashboard customization for external users
6. Extended API Integrations - Third-party integrations beyond explicitly defined ones
7. Undocumented Features - Any requirements not captured in official documentation

## Consideration
Item # | Area | Consideration | Status | Owner | Impact
| Requirements Traceability & Completeness | Cross-reference all user stories against wireframes - Ensure every admin, analyst, public, and external user story has corresponding wireframe implementation | Missing | Business Analyst | HIGH
| Requirements Traceability & Completeness | CRUD permissions matrix validation - Verify each role's create/read/update/delete permissions match wireframes | Missing | Dev/Security | HIGH
| Requirements Traceability & Completeness | Missing filter options - User stories mention filtering "any certificate field" but wireframes show limited filter options | Gap | UI/Dev | MEDIUM
| Requirements Traceability & Completeness | TODO item in requirements: "list all CRUD fields" - Admin user story references incomplete CRUD field documentation | Open | Business Analyst | HIGH
| Security & Compliance | Multi-factor authentication implementation - Required per admin user stories but no wireframes exist | Missing | Security/Dev | HIGH
| Security & Compliance | User activity logging - Required for audit trail but no UI for viewing logs | Missing | Dev | MEDIUM
| Security & Compliance | Data encryption standards - Not documented for certificate uploads and sensitive data | Missing | Security | HIGH
| Security & Compliance | Role-based access controls - Need detailed permission matrix for each user type | Incomplete | Security | HIGH
| Security & Compliance | Partner data segregation - Amazon vs Wayfair vs other partners need isolated access | Incomplete | Dev/Security | HIGH
| API & Integration Concerns | Amazon API testing timeline - Scheduled 6/16-6/27 but JSON format may need validation | At Risk | Dev/Integration | HIGH
| API & Integration Concerns | Product ID type changes in API - 4/30 version shows UPC/GTIN, 6/15 shows ASIN - which is correct? | Conflict | API Team | HIGH
| API & Integration Concerns | Multiple partner API support - Comments mention "multiple partners" but only Amazon API documented | Gap | Dev | MEDIUM
| API & Integration Concerns | API error handling and fallbacks - No documentation on failure scenarios | Missing | Dev | MEDIUM
| Data Management & Migration | Current database migration plan - How existing data transfers to new system | Missing | Dev/DBA | HIGH
| Data Management & Migration | Certificate numbering logic - Auto-generation with manual override needs clear rules | Unclear | Business/Dev | MEDIUM
| Data Management & Migration | Duplicate prevention - No validation rules for preventing duplicate certificates/products | Missing | Dev | MEDIUM
| Data Management & Migration | Data validation rules - Required field validation, format requirements not documented | Incomplete | Dev | MEDIUM
| Performance & Scalability | Infinite scroll implementation - Performance impact with thousands of certificates | Design Only | Dev | MEDIUM
| Performance & Scalability | Large product ID lists - Comments mention "thousands of ASINs" performance concerns | Identified | Dev/UX | HIGH
| Performance & Scalability | Search performance - No indexing strategy for certificate searches across all companies | Missing | DBA | MEDIUM
| Performance & Scalability | File upload limits - Certificate PDF size limits and storage strategy not defined | Missing | Dev/Infrastructure | MEDIUM
| Testing & Validation Strategy | Business Acceptance Testing plan - Scheduled 6/16-6/27 but test scenarios undefined | Missing | QA/Business | HIGH
| Testing & Validation Strategy | Cross-browser compatibility - No testing strategy for different browsers | Missing | QA | MEDIUM
| Testing & Validation Strategy | Mobile responsiveness validation - Wireframes show desktop only | Missing | QA/UI | MEDIUM
| Testing & Validation Strategy | ADA compliance testing - No accessibility validation plan | Missing | QA/Legal | HIGH
| Testing & Validation Strategy | Load testing strategy - No performance testing with multiple concurrent users | Missing | QA/Dev | MEDIUM
| User Experience & Accessibility | ADA compliance validation - Screen reader compatibility, keyboard navigation | Missing | UI/QA | HIGH
| User Experience & Accessibility | Mobile-first design - All wireframes appear desktop-focused | Gap | UI | MEDIUM
| User Experience & Accessibility | Error message standards - No consistent error handling across screens | Missing | UI/Dev | MEDIUM
| User Experience & Accessibility | Loading states and feedback - No wireframes show loading indicators or progress | Missing | UI | LOW
| User Experience & Accessibility | Keyboard shortcuts for power users - Analysts/admins may need efficiency features | Missing | UI | LOW
| Documentation & Training | User training materials - No plan for onboarding different user types | Missing | Training/Documentation | MEDIUM
| Documentation & Training | API documentation for partners - External partners need integration guides | Missing | Documentation | MEDIUM
| Documentation & Training | System administration guide - Managing roles, permissions, system settings | Missing | Documentation | MEDIUM
| Documentation & Training | Troubleshooting procedures - Support team needs issue resolution guides | Missing | Documentation | LOW
| Business Continuity | Backup and recovery strategy - Critical business data protection plan | Missing | Infrastructure | HIGH
| Business Continuity | Rollback procedures - Plan if new system has issues after go-live | Missing | Dev/Operations | HIGH
| Business Continuity | Data export capabilities - Business continuity if system changes needed | Partial | Dev | MEDIUM
| Business Continuity | Disaster recovery testing - Validation of backup/recovery procedures | Missing | Infrastructure | MEDIUM
| Go-Live Readiness | Production environment setup - Infrastructure readiness for 7/11 go-live | Unknown | Infrastructure | HIGH
| Go-Live Readiness | User acceptance sign-offs - Formal approval process from each user group | Missing | Business | HIGH
| Go-Live Readiness | Deployment checklist - Step-by-step go-live procedures (6/30-7/11) | Missing | Operations | HIGH
| Go-Live Readiness | Post-launch support plan - Immediate support for first weeks after launch | Missing | Support | MEDIUM

## Sitemap
Sitemap
Screen | Role/Category | FileName | Notes
1.0 Certificates | Public | 1_0_certificateViewTileFinal.html | User story updated to not include Certificate number. As a public user, I want to search for certifications by certificate number, certificate type, company, country or product so that I can verify compliance.
1.1 Single Certificate View | Public | 1_1_CertificateSingleView.html
2.0 Dashboard | External | 2_0_Dashboard.html
3.0 Certificates | External | 3_0_CertificateExternal.html
3.1 Single Certificate View | External | 3_1_CertificateInternalSingleView.html
3.2 Certificates | Analyst | 3_2_Certificate_GCC.html
3.3 Single Certificate View | Analyst | 3_3_CertificateInternalSingleView.html | 3.3 – This would be clients and partners
4.0 API Spec | Out of Scope |  | Future Phase
4.1 API User Settings | Out of Scope |  | Future Phase
4.2 API FAQ | Out of Scope |  | Future Phase
5.0 Companies & Products | Analyst | Nav Item only
5.1 Companies | Admin | 5_1_Company.html
5.2 Products | Admin | 7_4_3_ProductManagement.html
6.0 Login Screens | Shared | Nav Item only
6.1 Login | Shared | 0_1_Loginscreens.html
6.2 Forgot Password | Shared | 0_1_Loginscreens.html
6.3 Password Reset Confirmation | Shared | 0_1_Loginscreens.html
6.4 Reset Password | Shared | 0_1_Loginscreens.html
6.5 Password Reset Success | Shared | 0_1_Loginscreens.html
6.6 2FA Authenticate OTP | Shared | 0_1_Loginscreens.html
6.7 Sign-up Registration | Out of Scope |  | Future Phase
6.8 Notification & Alerts | Shared | 0_0_NotificationAlertsFinal.html
7.0 Administration | Admin | Nav Item only
7.1 Role Management | Admin | 7_1_RoleManagement.html
7.2 User Management | Admin | 7_1_1_UserManagement.html
7.3 Configuration/Settings | Admin | Nav Item only
7.3.1 Google Analytics / SEO | Admin | 7_2_2_GoogleAnalytics.html
7.3.2 Dashboard Configuration | Out of Scope |  | Future Phase (Retained
7.3.3 Clone Feature | Out of Scope |  | Future Phase
7.3.4 Excel Mass Upload | Out of Scope |  | Future Phase
7.4 API Management | Admin | Nav Item only
7.4.1 Amazon API Integration | Admin | 7_3_APIManagement.html
7.5 Data Management | Admin | Nav Item only
7.5.1 Certificate Types | Admin | 7_4_1_CertificateTypes.html | May need to add pages to edit/delete Product Name or Company Name records unless you can find another way
7.5.2 Product Types | Admin | 5_2_ProductTypes.html | May need to add pages to edit/delete Product Name or Company Name records unless you can find another way
7.5.3 Certificate Fields | Admin | 7_5_1_CertificateFieldManagement.html | Ability to add new fields for certficates. How will fields be displayed on page?
7.5.4 CSF Attributes | Admin | 7_5_2_CSFAttributes.html
7.5.5 Tags | Admin | 7_5_3_TagManagement.html
7.5.6 Partners | Admin | 7_5_4_Partners.html

## Final Design Cleanup Tracker
Issue Tracker
Item # | Type | Page/Context | GCC Comment | Status | Owner | Priority | Fix | Comments
0.1 | Design Fix | main.css, Layout, cert tile view |  |  |  |  | Tiles headers should be the same height
0.2 |  | Single Certificate view Public |  |  |  |  | Logo and title should be consistent across differernt media sizes.
0.3 |  | Single Certificate view External |  |  |  |  | Card tile content needs to be updated for real data. | The example that was provided in the mockup was to show the different content length to test that the max content would fit in the tiles. This was not meant to be inconsistent but shown to handle max content.
0.4 |  | Single Certificate View Internal | [5 empty] | CSS fixes for the different layouts. Tablet view should have collapsable filter and search like mobile. All Tiles header section should be the same height. The download icon and view icon should be at the bottom of the tile and consistently in the same place. Logo image, Title and subtext should be consistent in placement across all media types. Product Text should match the layout.png image
0.5 |  | main.css, Layout, cert tile view
0.6
0.7
0.8
0.9
10 | Design Fix | Filter Panel | “Missing Additional section (for external tags). As filter options right now you can add APR (Association of Plastic Recyclers), LEED” | Open | UI | Medium | APR and LEED tag filters are missing—must be added and traced in Requirements
1 | Design Fix | Global | “Fix alignment” (Mobile View, Option 4 – Final) | Open | UI | Medium | Align tiles or cards evenly in mobile layout
2 | Design Fix | Global | “Usually when this is open this becomes an X to close out” | Open | UI | Medium | Refers to dropdowns or slide-outs needing consistent open/close icons
3 | Design Fix | Global | “Give link styling” | Open | UI | Medium | Likely referring to missing underlines, colors, or hover states
4 | Design Fix | Global | “Does this get underline based on style guide and links in footer? Is blue color right?” | Open | UI | Medium | Needs confirmation of styling conventions for links
7 | Design Fix | Global | “Make sure you give more white padding around the exterior sides…” | Open | UI | Medium | Visual spacing issue—white box too close to gray edges
8 | Design Fix | Global | “Fix alignment” | Open | UI | Medium | Repeated—may apply to various screen sections
12 | Documentation | List all Crud Fields
9 | Design Fix | Certificate Search (Web View - Public?) | “Why is this here? There could be thousands listed. It’s not listed in wires. They can search cert number by typing in search bar” | Resolved | UI | Medium | This was added as it was listed in the user story. Even though it wasn't in the original wireframe. However, the change was incorrect and has been resolved. User story has also been updated. | User story updated to not include Certificate number. As a public user, I want to search for certifications by Certification Type, company, country or product so that I can verify compliance.
5 | Design Fix | Global | “Remove dot” | Resolved | UI | Medium | element issue removed. | none
6 | Design Fix | Global | “Just make sure all the font sizes are big enough… Should not have anything less than 12 point / 16 pixel in body area” | Resolved | UI | Medium | Minimum font size for accessibility compliance
11 | Design Fix | Filter Logic | “Make sure on real site all the filter options are alphabetical” | Resolved | UI | Medium | Functional sorting requirement
12 | Functional Requirement | Add Certificate (3.3) | Missing field: Partner (Amazon/Wayfair) - required. Need to add option of "none" and multi-select capability | Open | Dev | HIGH | Required field per meeting notes
13 | Functional Requirement | Add Certificate (3.3) | Missing field: Status Type - to signify if a client doesn't want to move forward | Open | Dev | HIGH | Added based on meeting requirements
16 | Functional Requirement | Add Certificate (3.3) | Missing field: Partner (Amazon/Wayfair) - required. Need to add option of "none" and multi-select capability | Open | Dev | HIGH |  | Required field per meeting notes
17 | Functional Requirement | Add Certificate (3.3) | Missing field: Status Type - to signify if a client doesn't want to move forward | Open | Dev | HIGH |  | Added based on meeting requirements
27 | Content Correction | Add Certificate (3.3) | Remove image section | Open | UI Team | MEDIUM |  | Unnecessary component
28 | Content Correction | Add Certificate (3.3) | Add record information to screenshot | Open | UI Team | MEDIUM |  | Missing data display
29 | Content Correction | Add Certificate (3.3) | Company info should auto-populate from Companies page when selecting company (not editable here) | Open | Dev | MEDIUM |  | Data consistency
26 | Content Correction | Add/Edit Certificate | Change "Product ID Manager" to "Products" | Open | UI Team | MEDIUM |  | Label consistency
14 | Design Fix | Certificate Field Management (7.5.1) | Action alignment issue - Update screenshot for alignment problems | Open | UI Team | HIGH | Noted in 6/15/25 version
18 | Design Fix | Certificate Field Management (7.5.1) | Action alignment issue - Update screenshot for alignment problems | Open | UI Team | HIGH |  | Noted in 6/15/25 version
20 | Functional Requirement | Certificate List External (3.0) | Partners vs Customers access - Partners should have access across companies for products under their program only (e.g., Amazon CPF clients/certs) | Open | Business/Dev | MEDIUM |  | Need clarification on requirements
21 | Functional Requirement | Certificate List External (3.0) | Move actions to left side of table | Open | UI Team | MEDIUM |  | UI improvement
22 | Functional Requirement | Certificate List External (3.0) | Can only see Internal tags if assigned - need requirement clarification | Open | Business | MEDIUM |  | Access permissions unclear
25 | Functional Requirement | Certificate List GCC (3.2) | Right align Add certificate button and make green primary to draw attention | Open | UI Team | LOW |  | Visual emphasis
36 | Design Fix | Certificate List GCC (3.2) | Add Edit icon for GCC users | Open | UI Team | MEDIUM |  | Missing visual element
37 | Design Fix | Certificate List GCC (3.2) | Update table based on how ASIN, UPC, etc. will be handled | Open | UI Team | MEDIUM |  | Data display clarification
24 | Functional Requirement | Certificate Lists | How to handle thousands of ASINs under a cert - may need Products page access for external users | Open | Business/Dev | MEDIUM |  | Scalability concern
39 | Design Fix | Certificate Lists | Update for infinite scrolling instead of pagination | Open | Dev | MEDIUM |  | Performance improvement
44 | Technical Requirement | Certificate Lists | Lazy loading - ability to load table as user scrolls rather than page control | Open | Dev | LOW |  | Wishlist item
35 | Usability Concern | Certificate Management | Product Category, Type, and Subcategory not editable on Add/Edit Certificate pages - assigned when adding new product | Open | Dev | LOW |  | Business rule clarification
41 | Technical Requirement | Certificate Management | Certification # auto-generated by database unless manually entered - need instructional copy like current DB | Open | Dev | MEDIUM |  | User guidance needed
15 | Content Correction | Company Management (5.1) | Company Contact should be separated into two fields: Email and Phone (separate from URL) | Open | Dev | HIGH | Current single field is insufficient
19 | Content Correction | Company Management (5.1) | Company Contact should be separated into two fields: Email and Phone (separate from URL) | Open | Dev | HIGH |  | Current single field is insufficient
32 | Usability Concern | Company Management (5.1) | Does information auto-populate under cert if listed here? If not using for auto-population, only need Company Name | Open | Business/Dev | MEDIUM |  | Data flow clarification
38 | Design Fix | CSF Attributes (7.5.2) | Should add buttons on this screen and all screens to integrate into the grid | Open | UI Team | MEDIUM |  | Consistency improvement
42 | Technical Requirement | CSF Attributes (7.5.2) | Should not need to import for this. Remove import button | Open | Dev | MEDIUM |  | Unnecessary functionality
43 | Technical Requirement | CSF Attributes (7.5.2) | Do we need this if you inline edit below? | Open | Dev | MEDIUM |  | Redundant functionality
33 | Usability Concern | Forgot Password (6.2) | Input field shows "Email or Username" - need clarification on which is accepted | Open | Dev | LOW |  | User input validation
30 | Content Correction | Login (6.1) | Remove icons from buttons - Forgot password should be grey, login should use lighter green | Open | UI Team | LOW |  | Visual cleanup
31 | Usability Concern | Navigation | Discuss this page - referenced in navigation wireframe | Open | Business | MEDIUM |  | Page purpose unclear
23 | Functional Requirement | Product ID Manager (5.3) | Partners and Clients should have access without add, edit, delete capabilities - view only based on their permissions | Open | Dev | MEDIUM |  | Access control requirement
40 | Design Fix | Public Certificate List (1.0) | Fields not included on Tile view: Company Contact Email/URL, Product Subcategory, Tags | Open | UI Team | LOW |  | Display completeness
34 | Usability Concern | Users Management (7.1) | Can only edit one user at a time - noted limitation | Open | Dev | LOW |  | Functional constraint

## User Stories
GCC Database User Stories and Requirements
Role | Category | User Story | Acceptance Criteria
Public | Access & Visibility | As a public user, I want to browse publicly available active certifications so that I can verify product compliance. | View only active, non-confidential certifications without login
Public | Access & Visibility | As a public user, I want to access certifications without needing to log in so that I can quickly find information. | No authentication required for public access
Public | Access & Visibility | As a public user, I want to view only non-confidential certifications so that I do not access restricted data. | Proper data filtering for public visibility
Public | Search & Filtering | As a public user, I want to search for certifications by certificate number, certificate type, company, country or product so that I can verify compliance. | Search functionality across key fields
Public | Search & Filtering | As a public user, I want to filter certifications by product, product type/category, and product subcategory so that I can narrow my search. | Filter controls for product categories
Public | Search & Filtering | As a public user, I want to see the most recently issued certifications and those with upcoming expiration dates. | Date-based sorting and filtering
Public | Viewing & Downloading | As a public user, I want to view details of a certification so that I can verify product compliance. | Single certificate detail view
Public | Viewing & Downloading | As a public user, I want to view and download single certifications so that I can reference them offline. | Certificate download functionality
Public | Tagging & Classification | As a public user, I want to view external tags on public certifications so that I can understand product categories. | External tag visibility only
Public | Tagging & Classification | As a public user, I want to filter by public tags so that I can refine my search results. | Public tag filtering capability
Public | Data Access & Security | As a public user, I want to access only non-confidential certification data so that privacy is maintained. | Public data filtering
Public | Data Access & Security | As a public user, I want to verify certificate authenticity so that I can trust the information. | Certificate verification features
External (Client) | Access & Visibility | As an external user, I want to log in securely so that I can access my company's certification data. | Secure authentication system
External (Client) | Access & Visibility | As an external user, I want to see all certifications related to my company so that I can track compliance. | Company-filtered data access
External (Client) | Access & Visibility | As an external user, I want to ensure that I cannot see certifications from other companies so that my access is restricted to my organization. | Proper access control and data isolation
External (Client) | Access & Visibility | As an external user, I want my permissions to be pre-defined by an admin so that I only access the relevant data. | Admin-controlled permission system
External (Client) | Access & Visibility | As an external user, I want to be able to filter my certifications based on status (active, expired, pending) so that I can quickly find relevant information. | Status-based filtering
External (Client) | Search & Filtering | As an external user, I want to search for certifications within my company so that I can locate specific records. | Company-scoped search functionality
External (Client) | Search & Filtering | As an external user, I want to filter certifications by type, category, and subcategory so that I can narrow down the results. | Multi-level filtering system
External (Client) | Search & Filtering | As an external user, I want to sort certifications by expiration date so that I can prioritize renewals. | Date sorting functionality
External (Client) | Search & Filtering | As an external user, I want to search certifications by product name so that I can verify specific items. | Product name search
External (Client) | Search & Filtering | As an external user, I want to filter by location, tags, and other available filter options based on their intended search purpose. | Advanced filtering options
External (Client) | Search & Filtering | As an external user, I want to export my company's certification data into Excel so that I can use it for reporting and documentation purposes. | Excel export functionality
External (Client) | Tagging & Classification | As an external user, I want to view external tags on certifications so that I can understand categorization. | External tag visibility
External (Client) | Tagging & Classification | As an external user, I want to filter by available tags so that I can narrow my search results. | Tag-based filtering
External (Client) | Data Access & Security | As an external user, I want my access to be restricted to only my company's data so that confidentiality is maintained. | Company-based access control
External (Client) | Data Access & Security | As an external user, I want to access the system securely so that my company's data is protected. | Secure authentication and session management
External (Partner) | Access & Visibility | As an external user, I want to log in securely so that I can access my program's certification data. | Secure authentication for partners
External (Partner) | Access & Visibility | As an external user, I want to see all certifications related to my program so that I can track compliance. | Program-filtered data access
External (Partner) | Access & Visibility | As an external user, I want to ensure that I cannot see certifications from other companies or programs so that my access is restricted to my program. | Partner-based access control
External (Partner) | Access & Visibility | As an external user, I want my permissions to be pre-defined by an admin so that I only access the relevant data. | Admin-managed partner permissions
External (Partner) | Access & Visibility | As an external user, I want to be able to filter my certifications based on status (active, expired, pending) so that I can quickly find relevant information. | Status filtering for partners
External (Partner) | Search & Filtering | As an external user, I want to search for certifications within my program so that I can locate specific records. | Program-scoped search
External (Partner) | Search & Filtering | As an external user, I want to filter certifications by type, category, and subcategory so that I can narrow down the results. | Category-based filtering
External (Partner) | Search & Filtering | As an external user, I want to sort certifications by expiration date so that I can prioritize renewals. | Expiration date sorting
External (Partner) | Search & Filtering | As an external user, I want to search certifications by product name so that I can verify specific items. | Product search capability
External (Partner) | Search & Filtering | As an external user, I want to filter by location, tags, and other available filter options based on their intended search purpose. | Location and tag filtering
External (Partner) | Search & Filtering | As an external user, I want to export my program certification data into Excel so that I can use it for reporting and documentation purposes. | Partner data export
External (Partner) | Tagging & Classification | As an external user, I want to view relevant tags for my program so that I can understand product categorization. | Program-specific tag visibility
External (Partner) | Tagging & Classification | As an external user, I want to filter by program-relevant tags so that I can find certifications efficiently. | Tag-based filtering for partners
External (Partner) | Data Access & Security | As an external user, I want my access to be restricted to only my partner program's data so that confidentiality is maintained. | Partner program access control
External (Partner) | Data Access & Security | As an external user, I want to access the system securely so that program data is protected. | Secure partner authentication
Analyst | Access & Visibility | As an analyst, I want to log in securely so that I can access certification data. | Analyst authentication
Analyst | Access & Visibility | As an analyst, I want to see all certifications so that I can manage records effectively. | Full certification access
Analyst | Access & Visibility | As an analyst, I want my access restricted to only my assigned role so that I do not see unauthorized data. | Role-based access control
Analyst | Access & Visibility | As an analyst, I want to view dashboard reports so that I can track data and trends. | Dashboard functionality
Analyst | Search & Filtering | As an analyst, I want to filter certifications by all fields so that I can generate reports and narrow by results based on my search needs. | Comprehensive filtering
Analyst | Search & Filtering | As an analyst, I want to sort certifications by modification date so that I can easily find a recent certificate that may need additional edits. | Modification date sorting
Analyst | Viewing & Downloading | As an analyst, I want to view detailed certification records so that I can ensure compliance accuracy. | Detailed record view
Analyst | Viewing & Downloading | As an analyst, I want to download certification data in bulk so that I can conduct offline analysis. | Bulk download capability
Analyst | Viewing & Downloading | As an analyst, I want to see the history of modifications for a certification so that I can track changes. | Change history tracking
Analyst | Viewing & Downloading | As an analyst, I want to download multiple certifications based on search criteria to view or save in bulk. | Bulk export based on filters
Analyst | Tagging & Classification | As an analyst, I want to apply existing tags to certifications so that I can organize data effectively. | Tag application capability
Analyst | Tagging & Classification | As an analyst, I want to view all available tags and categories so that I can use consistent classification. | Tag visibility and reference
Analyst | Data Access & Security | As an analyst, I want to securely access internal certification data so that I can perform my analysis duties. | Secure data access
Analyst | Data Access & Security | As an analyst, I want my actions to be logged so that there is an audit trail of my activities. | Activity tracking
Admin | Access & Visibility | As an admin, I want to manage user roles and permissions so that I can control access levels. | User role management system
Admin | Access & Visibility | As an admin, I want to view all certifications across all companies so that I can oversee compliance. | Global certification access
Admin | Access & Visibility | As an admin, I want to create, edit, and delete user accounts so that I can manage system access. | User account CRUD operations
Admin | Search & Filtering | As an admin, I want to search certifications across all companies so that I can manage records efficiently. | Global search capability
Admin | Search & Filtering | As an admin, I want to filter any of the certificate fields so that I can oversee compliance trends. | Universal field filtering
Admin | Search & Filtering | As an admin, I want to sort certifications by the last modified date so that I can track updates. | Last modified sorting
Admin | Search & Filtering | As an admin, I want to be able to set the certificate status (active, expired, pending). | Status management
Admin | Viewing & Downloading | As an admin, I want to view detailed certification records across the entire platform so that I can manage data integrity. | Platform-wide record access
Admin | Viewing & Downloading | As an admin, I want to export all certification data so that I can generate system-wide reports. | Complete data export
Admin | Viewing & Downloading | As an admin, I want to track certification history and changes so that I can audit modifications. | Audit trail functionality
Admin | Tagging & Classification | As an admin, I want to create, edit, and remove tags so that I can organize certifications effectively. | Tag management system
Admin | Tagging & Classification | As an admin, I want to standardize tags across the platform so that users have consistent classification options. | Tag standardization
Admin | Tagging & Classification | As an admin, I'm the only role that has the ability to edit product categories, product types and subcategories, certification types, CSF attributes. | Exclusive admin editing rights
Admin | Tagging & Classification | As an admin, I have the ability to add new fields. | Dynamic field creation
Admin | Data Access & Security | As an admin, I want to enforce multi-factor authentication so that system security is enhanced. | MFA implementation
Admin | Data Access & Security | As an admin, I want to track user activity logs so that I can monitor system usage. | Activity logging
Admin | Data Access & Security | As an admin, I want the ability to add a new field to certificates. | Field customization
Admin | Data Access & Security | As an admin, I want to restrict access to certain certifications so that only authorized users can view them. | Access restriction controls
Admin | Data Access & Security | As an admin, I want to integrate API connections with third-party platforms so that external vendors can securely access data. | API integration management
Admin | Data Access & Security | As an admin, I want the ability to add, update or delete data for product types, certificate types, partners, CSF Attributes, etc. | Master data CRUD operations
Admin | Data Access & Security | As an admin, I want the system back-end to manage what appears in the public database based on active status. | Automated public visibility
Admin | Data Access & Security | As an admin, I want the system back-end to handle certificate numbering with manual override option available if needed. | Certificate numbering system

## Requirements(old-archive) (hidden)
Requirements
Item # | Requirement Type | Field Name | Type | Required | Notes | Access Level
1 | Database Field Requirements | Certificate # | Text | Yes | Auto-generated if left blank | All
2 | Database Field Requirements | Certification Type | Dropdown | Yes | Type of certification issued | All
3 | Database Field Requirements | CSF Attributes | Multi-Select | Optional | Certification specific framework attributes | All
4 | Database Field Requirements | Status | Dropdown | Yes | Required for public visibility (Active/Expired/Pending) | All
5 | Database Field Requirements | Effective Date | Date | Yes | When the certification becomes effective | All
6 | Database Field Requirements | Expiration Date | Date | Yes | When the certification expires | All
7 | Database Field Requirements | Company | Text | Yes | Company receiving certification | All
8 | Database Field Requirements | Company Contact Email | Text | Optional | Contact email for company | Internal only
9 | Database Field Requirements | Company Contact URL | Text | Optional | Company website | All
10 | Database Field Requirements | Product Name | Text | Optional | Name of certified product | All
11 | Database Field Requirements | Product Category | Dropdown | Required when Product Name exists | Product classification | All
12 | Database Field Requirements | Product Type | Dropdown | Required when Product Name exists | Product type classification | All
13 | Database Field Requirements | Product Type Subcategory | Dropdown | Optional | Product subcategory | All
14 | Database Field Requirements | Location | Text | Yes | Geographic location | All
15 | Database Field Requirements | Country | Text | Yes | Country of certification | All
16 | Database Field Requirements | External Tag | Text | Optional | Public-facing tags | All
17 | Database Field Requirements | Internal Tag | Text | Optional | Internal use tags | Internal only
18 | Database Field Requirements | ASIN | Text | Optional | Amazon product identifier | Internal only
19 | Database Field Requirements | UPC | Text | Optional | Universal Product Code | Internal only
20 | Database Field Requirements | GTIN | Text | Optional | Global Trade Item Number | Internal only
21 | Database Field Requirements | EAN | Text | Optional | European Article Number | Internal only
22 | Database Field Requirements | Certificate Upload | File | Optional | Certificate document | All
23 | Database Field Requirements | Partner | Dropdown | Required | Amazon/Wayfair partnership designation | Internal only
24 | Database Field Requirements | Record Created Date | Date | Auto-generated | System generated | Internal only
25 | Database Field Requirements | Record Last Updated Date | Date | Auto-generated | System generated | Internal only
26 | Database Field Requirements | Last Edited By | Text | Auto-generated | User who made last edit | Internal only
27 | Database Field Requirements | Preview | Link | Auto-generated | Certificate preview link | All
| Technical Requirements |  |  |  | Multi-factor authentication support
| Technical Requirements |  |  |  | User activity logging
| Technical Requirements |  |  |  | API integration capabilities for third-party platforms
| Technical Requirements |  |  |  | Excel export functionality for filtered results
| Technical Requirements |  |  |  | Bulk download capabilities
| Technical Requirements |  |  |  | Change history tracking
| Technical Requirements |  |  |  | Lazy loading for large datasets (infinite scrolling)
| Technical Requirements |  |  |  | Mobile responsive design
| Technical Requirements |  |  |  | Certificate verification URL display
| Technical Requirements |  |  |  | Inline editing capabilities for admin functions
| Technical Requirements |  |  |  | New tab loading for certificate views
| Technical Requirements |  |  |  | Left-aligned action buttons in tables
| Functional Requirements | Certificate Type |  | Yes
| Functional Requirements | Status |  | Yes
| Functional Requirements | Effective Date |  | Yes
| Functional Requirements | Expiration Date |  | Yes
| Functional Requirements | Company |  | Yes
| Functional Requirements | Location |  | Yes
| Functional Requirements | Country |  | Yes
| Functional Requirements | Partner |  | Yes
| Functional Requirements | Product Category (when Product Name exists) |  | Yes
| Functional Requirements | Product Type (when Product Name exists) |  | Yes
| System Generated | Certificate # (if not manually entered)
| System Generated | Record Created Date
| System Generated | Record Last Updated Date
| System Generated | Last Edited By
| Business Rules | N/A options required for: Product Category, Product Type, Subcategory, Partner
| Business Rules | System automatically removes expired and inactive certificates from public view
| Business Rules | Company contact fields pulled from companies page
| Business Rules | CSF Attributes only show when selected for a certification
| Business Rules | Record Information only available for Analyst and Admin roles
| Business Rules | Products section shows only products under the certificate being viewed
| Business Rules | Product Category, Type, and Subcategory not editable on certificate edit page
| Business Rules & Validations | Public Database: Only active status certificates appear publicly
| Business Rules & Validations | Partner Access: Partners see only program-specific certifications across companies
| Business Rules & Validations | Client Access: Clients restricted to their company's certifications only
| Business Rules & Validations | Internal Access: Analysts and Admins see record creation/update information
| Business Rules & Validations | CSF Attributes: Only display when selected for specific certifications
| System Automation | Certificate Numbering: Auto-generated with manual override capability
| System Automation | Contact Information: Pulled from company pages automatically
| System Automation | Public Visibility: Expired and inactive certificates automatically hidden from public view
| System Automation | Record Tracking: System automatically tracks creation dates, last updates, and editors
| Data Entry Validations | Required Field Enforcement: Certificate Type, Status, Effective Date, Expiration Date, Company, Location, Country, Partner
| Data Entry Validations | Conditional Requirements: Product Category and Type required when Product Name exists
| Data Entry Validations | N/A Options: Available for Product Category, Type, Subcategory, and Partner fields
| Data Entry Validations | Email Validation: Required format validation for company contact emails
| Data Entry Validations | Date Logic: Expiration date must be after effective date

## Sheet14
GCC Database Requirements - Complete Master Table | [6 empty] | Access Level Legend:
Item # | Category | Requirement Name | Type | Required | Access Level | Notes/Description | All = Public, External Client/Partner, Analyst, Admin
1 | Database Field | Certificate # | Text | Yes | All | Auto-generated if left blank | Internal Only = Analyst, Admin only
2 | Database Field | Certification Type | Dropdown | Yes | All | Type of certification issued | Public = Public users only
3 | Database Field | CSF Attributes | Multi-Select | Optional | All | Certification specific framework attributes | Partner = External Partners only
4 | Database Field | Status | Dropdown | Yes | All | Required for public visibility (Active/Expired/Pending) | Client = External Clients only
5 | Database Field | Effective Date | Date | Yes | All | When the certification becomes effective
6 | Database Field | Expiration Date | Date | Yes | All | When the certification expires
7 | Database Field | Company | Text | Yes | All | Company receiving certification
8 | Database Field | Company Contact Email | Text | Optional | Internal Only | Contact email for company
9 | Database Field | Company Contact URL | Text | Optional | All | Company website
10 | Database Field | Product Name | Text | Optional | All | Name of certified product
11 | Database Field | Product Category | Dropdown | Conditional | All | Product classification (Required when Product Name exists)
12 | Database Field | Product Type | Dropdown | Conditional | All | Product type classification (Required when Product Name exists)
13 | Database Field | Product Type Subcategory | Dropdown | Optional | All | Product subcategory
14 | Database Field | Location | Text | Yes | All | Geographic location
15 | Database Field | Country | Text | Yes | All | Country of certification
16 | Database Field | External Tag | Text | Optional | All | Public-facing tags
17 | Database Field | Internal Tag | Text | Optional | Internal Only | Internal use tags
18 | Database Field | ASIN | Text | Optional | Internal Only | Amazon product identifier
19 | Database Field | UPC | Text | Optional | Internal Only | Universal Product Code
20 | Database Field | GTIN | Text | Optional | Internal Only | Global Trade Item Number
21 | Database Field | EAN | Text | Optional | Internal Only | European Article Number
22 | Database Field | Certificate Upload | File | Optional | All | Certificate document
23 | Database Field | Partner | Dropdown | Yes | Internal Only | Amazon/Wayfair partnership designation
24 | Database Field | Record Created Date | Date | Auto-generated | Internal Only | System generated
25 | Database Field | Record Last Updated Date | Date | Auto-generated | Internal Only | System generated
26 | Database Field | Last Edited By | Text | Auto-generated | Internal Only | User who made last edit
27 | Database Field | Preview | Link | Auto-generated | All | Certificate preview link
28 | Technical | Multi-factor Authentication Support | System | Required | Internal Only | Enhanced security authentication
29 | Technical | User Activity Logging | System | Required | Internal Only | Track and monitor system usage
30 | Technical | API Integration Capabilities | System | Required | Internal Only | Third-party platform connectivity
31 | Technical | Excel Export Functionality | Feature | Required | All | Export filtered results to Excel
32 | Technical | Bulk Download Capabilities | Feature | Required | All | Certificate batch download
33 | Technical | Change History Tracking | System | Required | Internal Only | Audit trail for modifications
34 | Technical | Lazy Loading for Large Datasets | Feature | Required | All | Infinite scrolling implementation
35 | Technical | Mobile Responsive Design | System | Required | All | Cross-device compatibility
36 | Technical | Certificate Verification URL Display | Feature | Required | All | Display verification links
37 | Technical | Inline Editing Capabilities | Feature | Required | Internal Only | Admin function editing
38 | Technical | New Tab Loading for Certificate Views | Feature | Required | All | Certificate views open in new tabs
39 | Technical | Left-aligned Action Buttons in Tables | UI | Required | All | Consistent button placement
40 | Functional | Certificate Type | Field | Yes | All | Required functional field
41 | Functional | Status | Field | Yes | All | Required functional field
42 | Functional | Effective Date | Field | Yes | All | Required functional field
43 | Functional | Expiration Date | Field | Yes | All | Required functional field
44 | Functional | Company | Field | Yes | All | Required functional field
45 | Functional | Location | Field | Yes | All | Required functional field
46 | Functional | Country | Field | Yes | All | Required functional field
47 | Functional | Partner | Field | Yes | Internal Only | Required functional field
48 | Functional | Product Category (when Product Name exists) | Field | Conditional | All | Required when Product Name exists
49 | Functional | Product Type (when Product Name exists) | Field | Conditional | All | Required when Product Name exists
50 | System Generated | Certificate # (if not manually entered) | Auto | System | All | Auto-generated certificate number
51 | System Generated | Record Created Date | Auto | System | Internal Only | System tracks creation date
52 | System Generated | Record Last Updated Date | Auto | System | Internal Only | System tracks last update
53 | System Generated | Last Edited By | Auto | System | Internal Only | System tracks editor
54 | Business Rules | N/A Options Required | Rule | System | All | For Product Category, Product Type, Subcategory, Partner
55 | Business Rules | Auto-Remove Expired Certificates | Rule | System | Public | System automatically removes expired and inactive certificates from public view
56 | Business Rules | Company Contact Fields Auto-Pull | Rule | System | All | Company contact fields pulled from companies page
57 | Business Rules | CSF Attributes Conditional Display | Rule | System | All | CSF Attributes only show when selected for a certification
58 | Business Rules | Record Information Access Control | Rule | System | Internal Only | Record Information only available for Analyst and Admin roles
59 | Business Rules | Products Section Filtering | Rule | System | All | Products section shows only products under the certificate being viewed
60 | Business Rules | Product Category Edit Restriction | Rule | System | All | Product Category, Type, and Subcategory not editable on certificate edit page
61 | Business Rules & Validations | Public Database Active Only | Rule | System | Public | Only active status certificates appear publicly
62 | Business Rules & Validations | Partner Access Control | Rule | System | Partner | Partners see only program-specific certifications across companies
63 | Business Rules & Validations | Client Access Restriction | Rule | System | Client | Clients restricted to their company's certifications only
64 | Business Rules & Validations | Internal Access Privileges | Rule | System | Internal Only | Analysts and Admins see record creation/update information
65 | Business Rules & Validations | CSF Attributes Display Control | Rule | System | All | Only display when selected for specific certifications
66 | System Automation | Certificate Numbering | Auto | System | All | Auto-generated with manual override capability
67 | System Automation | Contact Information Auto-Pull | Auto | System | All | Pulled from company pages automatically
68 | System Automation | Public Visibility Management | Auto | System | Public | Expired and inactive certificates automatically hidden from public view
69 | System Automation | Record Tracking | Auto | System | Internal Only | System automatically tracks creation dates, last updates, and editors
70 | Data Entry Validations | Required Field Enforcement | Validation | System | All | Certificate Type, Status, Effective Date, Expiration Date, Company, Location, Country, Partner
71 | Data Entry Validations | Conditional Requirements | Validation | System | All | Product Category and Type required when Product Name exists
72 | Data Entry Validations | N/A Options Availability | Validation | System | All | Available for Product Category, Type, Subcategory, and Partner fields
73 | Data Entry Validations | Email Validation | Validation | System | All | Required format validation for company contact emails
74 | Data Entry Validations | Date Logic Validation | Validation | System | All | Expiration date must be after effective date

## CRUD Operations
CRUD Operations by Role
Entity/Feature Area | Group | Details | Availability | Public | External Client | External Partner | Analyst | Admin
Certificates |  |  |  | Read (Active only) | Read (Company filtered) | Read (Partner filtered) | Read/Create/Update | Full CRUD
Companies |  |  |  | Read (Basic info) | Read (Own company) | Read (Partner companies) | Read | Full CRUD
Products |  |  |  | Read (Active certs) | Read (Company products) | Read (Partner products) | Read/Create/Update | Full CRUD
Users |  |  |  | None | None | None | None | Full CRUD
Certificate Types |  |  |  | Read | Read | Read | Read | Full CRUD
Product Types |  |  |  | Read | Read | Read | Read | Full CRUD
Tags |  |  |  | Read (External only) | Read | Read | Read | Full CRUD
CSF Attributes |  |  |  | Read | Read | Read | Read | Full CRUD
Partners |  |  |  | None | None | None | None | Full CRUD
Role Management | Administrative Management | Page-level access control for all roles | Admin Only
User Management | Administrative Management | Add, edit, delete user accounts with role assignment | Admin Only
Product ID Management | Administrative Management | ASIN, UPC, GTIN, EAN identifier management | Admin Only
Company Management | Administrative Management | Company details with separate contact email and phone fields | Admin Only
Certificate Field Management | Administrative Management | Dynamic field creation and editing with inline controls | Admin Only
API Management | Administrative Management | Third-party integration management (Draft phase) | Admin Only
List vs Tile View | View and Display Options | Toggle between list and tile display formats | External, Analyst, Admin
Infinite Scrolling | View and Display Options | Lazy loading instead of pagination | All Users
Column Sorting | View and Display Options | Sort on any available column | All Users
Horizontal/Vertical Scrolling | View and Display Options | Access additional data fields | All Users
Multi-select Operations | View and Display Options | Bulk selection for downloads and actions | All Users
Action Positioning | View and Display Options | Actions moved to left side of tables | All Users
Multiple ID Types | Product ID Management System | Support for ASIN, UPC, GTIN, EAN identifiers | Admin managed
Search & Filter | Product ID Management System | Find products by ID type, status, partner | Admin Only
Status Tracking | Product ID Management System | Active/Inactive status for each product ID | Admin Only
Partner Association | Product ID Management System | Link IDs to specific partners (Amazon, Wayfair) | Admin Only
Bulk Operations | Product ID Management System | Import/Export capabilities for ID management | Admin Only
Cross-linking | Product ID Management System | Multiple identifier types for same product | Admin Only
Reference Management | System Navigation & UX | Navigation-only, not a full page | System feature
Certificate Tabs | System Navigation & UX | Load certificate views in new tabs | All Users
Mobile Responsiveness | System Navigation & UX | Full mobile optimization | All Users
Verification URLs | System Navigation & UX | Display at bottom of certificate pages | Public feature

## Permissions (CRUD)
GCC Database Master CRUD Operations & Permissions Table
Category | Entity/Feature | Group | Details | Public | External Client | External Partner | Analyst (GCC User) | Admin | Security/Access Notes | User Story Reference | Screen Reference
Core Data | Certificates | Data Management | Certificate records | Read (Active only) | Read (Company filtered) | Read (Partner filtered) | Read/Create/Update | Full CRUD | MFA required for authenticated users; External users see all statuses for assigned data | Public: Search and view certification info; External Client: See all company certifications, track compliance; External Partner: See all program certifications; Analyst: View detailed records, ensure accuracy, modify records; Admin: View all certifications, oversee compliance, track changes, audit modifications | 1.0 Public Certificate View, 3.0 External Certificate List, 3.1 External Single Certificate View, 2.0 Dashboard, 3.3 Add Certificate, 3.4 Edit/Delete Certificate
Core Data | Companies | Data Management | Company information | Read (Basic info) | Read (Own company) | Read (Partner companies) | Read/Create/Update | Full CRUD | Client assignment by Admin; Multiple companies per client allowed | External Client: See company certifications, track compliance; Analyst: Add/edit companies; Admin: Create, edit, delete user accounts, manage system access | 5.0 Company Management
Core Data | Products | Data Management | Product records | Read (Active certs) | Read (Company products) | Read (Partner products) | Read/Create/Update | Full CRUD | Product categories/types Admin-managed only | External Client: Verify specific items; External Partner: See program products; Analyst: Add/edit products; Admin: Manage data integrity | 5.0 Product Management, 3.3 Add Certificate (Product ID Manager)
Core Data | Users | User Management | User accounts | None | None | None | None | Full CRUD | Admin-only user creation; No self-registration; Password recovery available | Admin: Manage user roles and permissions, control access levels, create/edit/delete user accounts | 7.1.1 User Management
Core Data | Certificate Types | Reference Data | Certification categories | Read | Read | Read | Read | Full CRUD | Admin-only editing of reference data | Admin: Only role to edit certification types | 7.5.1 Certificate Field Management
Core Data | Product Types | Reference Data | Product type definitions | Read | Read | Read | Read | Full CRUD | Admin-only editing of reference data | Admin: Only role to edit product types & subcategories | 7.5.1 Certificate Field Management
Core Data | Product Categories | Reference Data | Product categorization | Read | Read | Read | Read | Full CRUD | Admin-only editing of reference data | Admin: Only role to edit product categories | 7.5.1 Certificate Field Management
Core Data | Tags | Content Organization | Internal/External tags | Read (External only) | Read (External only) | Read (External only) | Read (All tags) | Full CRUD | External users see external tags only; Internal users see all | External: Filter by available tags; Analyst: View all tags; Admin: Create, edit, remove tags, standardize tags | All certificate views, 3.3 Add Certificate, 7.5.1 Certificate Field Management
Core Data | CSF Attributes | Reference Data | CSF certification attributes | Read | Read | Read | Read | Full CRUD | Admin-only editing of reference data | Admin: Only role to edit CSF attributes | 7.5.1 Certificate Field Management
Core Data | Partners | Reference Data | Partner organizations (Amazon/Wayfair) | None | None | None | None | Full CRUD | Partner field required for new certificates | Admin: Add, update or delete data for partners | 3.3 Add Certificate, 7.5.1 Certificate Field Management
Admin Functions | Role Management | Administrative Management | Page-level access control for all roles | None | None | None | None | Admin Only | Controls which roles access which pages | Admin: Manage which roles have access to which pages | 7.1 Role Management
Admin Functions | User Management | Administrative Management | Add, edit, delete user accounts with role assignment | None | None | None | None | Admin Only | Admin assigns external user permissions by company/partner | Admin: Create, edit, delete user accounts, manage system access | 7.1.1 User Management
Admin Functions | Product ID Management | Administrative Management | ASIN, UPC, GTIN, EAN identifier management | None | None | None | None | Admin Only | Multiple ID types per product; Partner associations | Admin: Product identifier management | 3.3 Add Certificate (Product ID Manager)
Admin Functions | Company Management | Administrative Management | Company details with separate contact email and phone fields | None | None | None | None | Admin Only | Manages company assignments for external clients | Admin: Company management | 5.0 Company Management
Admin Functions | Certificate Field Management | Administrative Management | Dynamic field creation and editing with inline controls | None | None | None | None | Admin Only | Can add/delete/rename database fields | Admin: Add new fields, ability to add/delete/rename fields | 7.5.1 Certificate Field Management
Admin Functions | API Management | Administrative Management | Third-party integration management (Draft phase) | None | None | None | None | Admin Only | Secure API connections for external vendors | Admin: Integrate API connections with third-party platforms | API wireframes (referenced but not detailed)
Security | Authentication | System Security | Email/Password login | No | Required | Required | Required | Required | MFA enforced; Admin creates all accounts | External Client: Log in securely; External Partner: Log in securely; Analyst: Log in securely; Admin: Enforce multi-factor authentication | 6.1 Login
Security | Multi-Factor Authentication | System Security | OTP/Authenticator app with backup methods | No | Configurable | Configurable | Configurable | Configurable | SMS/email backup options available | Admin: Enforce multi-factor authentication, enhance system security | 6.6 2FA Authenticate OTP
Security | Session Management | System Security | Secure session handling | No | Yes | Yes | Yes | Yes | Secure session tokens and timeout | All authenticated users | All authenticated screens
Security | Activity Logging | System Security | User activity tracking and audit logs | No | Logged | Logged | Logged | View/Manage | Admin can monitor all user actions | Admin: Track user activity logs, monitor system usage | System feature (no specific wireframe)
Security | Access Control | System Security | Role-based permissions enforcement | Public access | Company-filtered | Partner-filtered | Full internal | System admin | Data isolation by role and assignment | All users: Access restricted to assigned role | All screens
Display Options | List vs Tile View | View and Display Options | Toggle between list and tile display formats | No | Yes | Yes | Yes | Yes | UI preference setting
Display Options | Infinite Scrolling | View and Display Options | Lazy loading instead of pagination | Yes | Yes | Yes | Yes | Yes | Performance optimization
Display Options | Column Sorting | View and Display Options | Sort on any available column | Yes | Yes | Yes | Yes | Yes | Available on all accessible columns
Display Options | Horizontal/Vertical Scrolling | View and Display Options | Access additional data fields | Yes | Yes | Yes | Yes | Yes | Responsive design for all screen sizes
Display Options | Multi-select Operations | View and Display Options | Bulk selection for downloads and actions | No | Yes | Yes | Yes | Yes | Public limited to single selections
Display Options | Certificate Tabs | View and Display Options | Load certificate views in new tabs | Yes | Yes | Yes | Yes | Yes | Browser tab management
Display Options | Mobile Responsiveness | View and Display Options | Full mobile optimization | Yes | Yes | Yes | Yes | Yes | Responsive across all devices
Downloads | Certificate PDF | Export Functionality | Individual certificate downloads | Single only | Multi-select | Multi-select | Multi-select | Multi-select | Public restricted to single downloads
Downloads | List Export | Export Functionality | Excel export of certificate lists | No | Yes | Yes | Yes | Yes | Full data export for authorized users
Downloads | Bulk Operations | Export Functionality | Mass download capabilities | No | Yes (assigned data) | Yes (partner data) | Yes (all data) | Yes (all data) | Data filtered by user permissions
Product IDs | Multiple ID Types | Product ID Management System | Support for ASIN, UPC, GTIN, EAN identifiers | Read only | Read assigned | Read partner | Read all | Admin managed | Multiple identifiers per product allowed
Product IDs | Search & Filter | Product ID Management System | Find products by ID type, status, partner | Basic search | Company search | Partner search | Full search | Admin search | Search scope limited by role permissions
Product IDs | Status Tracking | Product ID Management System | Active/Inactive status for each product ID | Active only | All statuses (assigned) | All statuses (partner) | All statuses | Admin managed | Status determines public visibility
Product IDs | Partner Association | Product ID Management System | Link IDs to specific partners (Amazon, Wayfair) | No access | No access | View assigned | View all | Admin managed | Required field for new certificates
Product IDs | Bulk Operations | Product ID Management System | Import/Export capabilities for ID management | No access | No access | No access | No access | Admin only | Mass data management tools
Product IDs | Cross-linking | Product ID Management System | Multiple identifier types for same product | View only | View assigned | View partner | View all | Admin managed | Product can have multiple ID types
System Features | Reference Management | System Navigation & UX | Navigation-only, not a full page | System feature | System feature | System feature | System feature | System feature | Internal navigation system
System Features | Certificate Auto-numbering | System Processing | Automatic certificate number generation | System feature | System feature | System feature | System feature | Admin override | System generates with manual override option
System Features | Status-based Display | System Processing | Public database shows active certificates only | System feature | System feature | System feature | System feature | Admin controlled | Backend manages public visibility
System Features | Verification URLs | System Navigation & UX | Display at bottom of certificate pages | Public feature | Public feature | Public feature | System feature | System feature | Public verification capability
Dashboard | Dashboard Access | Analytics and Reporting | Dashboard reports and metrics | No | No | No | Yes | Yes | Internal users only
Dashboard | Report Generation | Analytics and Reporting | Custom reports and data analysis | No | Basic export | Basic export | Advanced reports | Full analytics | Reporting capabilities by role
Field Access | Public Fields | Data Visibility | Certificate #, Company, Product, Category, Type, Dates, Location, External Tags | Yes | Yes | Yes | Yes | Yes | Base field set for all users
Field Access | Extended Fields | Data Visibility | + Contact info, Product IDs, CSF Attributes, Status | No | Yes | Yes | Yes | Yes | Additional fields for authenticated users
Field Access | Internal Fields | Data Visibility | + Internal Tags, Audit trail, Modification history | No | No | No | Yes | Yes | Internal operational data
Field Access | Admin Fields | Data Visibility | + System configuration, User management data | No | No | No | No | Yes | System administration data
Out of Scope | Notifications & Alerts | Excluded Features | System notifications and real-time updates | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | Not included in initial scope
Out of Scope | Clone Feature | Excluded Features | Certificate cloning with selective field carry-over | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | Future enhancement
Out of Scope | Bulk Upload for Product IDs | Excluded Features | File upload for ASIN, UPC, GTIN, EAN bulk upload | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | Not available in initial scope
Out of Scope | Product-Specific Fields | Excluded Features | Additional ASIN-specific product data fields | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | May appear in wireframes for planning
Out of Scope | Customized Dashboard Widgets | Excluded Features | External user customizable reporting widgets | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | Basic dashboard only
Out of Scope | Extended Third-Party APIs | Excluded Features | Integrations beyond explicitly defined APIs | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | EXCLUDED | Amazon API only in scope
Validation | Required Fields | Data Validation | Cert Type, Status, Effective Date, Expiration Date, Company, Location, Country, Partner | N/A | N/A | N/A | Enforced | Enforced | Conditional requirements apply
Validation | Conditional Requirements | Data Validation | Product Category/Type required when Product Name exists | N/A | N/A | N/A | Enforced | Enforced | Business rule validation
Validation | N/A Options | Data Validation | N/A options for Product Category, Product Type, Subcategory, Partner | N/A | N/A | N/A | Available | Available | Handles null/empty values
Validation | Auto-Population | Data Validation | Company contact info auto-populated from Companies table | System feature | System feature | System feature | System feature | System feature | Prevents data inconsistency
Validation | Certificate Numbering | Data Validation | Auto-generated if not manually entered | System feature | System feature | System feature | Manual override | Manual override | Requires instructional copy
Validation | Expired Certificate Removal | System Processing | Auto-remove expired/inactive certs from public view | System feature | System feature | System feature | System feature | Admin controlled | Backend automation
UI Features | Inline Editing | User Interface | All field edits performed inline | No | No | No | No | Yes | Certificate Field Management only
UI Features | Product Image Upload | User Interface | Upload product images (under consideration) | No | No | No | Under review | Under review | Decision pending
UI Features | Action Position | User Interface | Actions moved to left side of tables | Yes | Yes | Yes | Yes | Yes | UI standard across all views
UI Features | Default View | User Interface | List view as default display | Yes | Yes | Yes | Yes | Yes | User can toggle to tile view
UI Features | Preview Function | User Interface | Eye icon for certificate preview | Yes | Yes | Yes | Yes | Yes | Quick view without opening full record
Business Rules | CSF Attributes | Data Processing | Shows only when selected for a certification | Conditional | Conditional | Conditional | Conditional | Conditional | Not required field
Business Rules | Company Contact Fields | Data Processing | Separate URL, Email, and Phone fields | Yes | Yes | Yes | Yes | Yes | Must be separate fields, not combined
Business Rules | Products Display | Data Processing | Show only products under certificate being viewed | Yes | Yes | Yes | Yes | Yes | Context-specific product listing
Business Rules | Product Association | Data Processing | Dropdown existing products or add new | No | No | No | Yes | Yes | Product categories not editable in certificate form
Business Rules | Record Information | Data Visibility | Creation date, last modified, modified by | No | No | No | Yes | Yes | Audit trail for internal users
Business Rules | Partner Multi-select | Data Processing | Multiple partner selection and "none" option | N/A | N/A | View only | Edit capability | Full management | Updated requirement from single select

## Scope Creep Summary
GCC Database Project – Scope Creep Summary
Area | Description | Timeline Impact
Client Requirements | User stories and requirements evolved during design. | +8 weeks
Front-End Redesign | Expanded from basic UI to 60+ wireframes and responsive design. | +5–6 weeks
Amazon API Integration | Added detailed field mapping and bi-directional calls. | +1–2 weeks
Product & Bulk Upload | Introduced multi-ID types (ASIN, UPC, GTIN, EAN) and import features. | +2–3 weeks
Field Management | Included inline editing and dynamic field creation. | +2 weeks
Role Management | Introduced 4 user roles with granular permissions. | +1–2 weeks
Dashboards | Added 10+ metrics, tracking, and role-based views. | +1–2 weeks
Stakeholder Feedback | Multiple rounds of design revisions required. | +3–4 weeks
Metric | Original | Revised | Increase
Timeline | 14–18 weeks | 34–40 weeks | +20–22 weeks