## Slide 1
ANUKI CONSULTING
Amazon API Integration Timeline
GCC Database Solution — Milestone Schedule & Risk Assessment
Prepared for GreenCircle Certified
April 15, 2026
CONFIDENTIAL

## Slide 2
Executive Summary
Amazon has requested firm milestone dates for API integration and automated product badging.
This document presents two timeline options with dependencies, risk factors, and mitigation strategies.
Both options are achievable contingent on completing the current UAT cycle without significant new scope.
API Infrastructure
Endpoints, authentication, and GS1 data schema are already built and tested. Amazon pulls data from our API.
Database Stabilization
40 items in final UAT retest. Must complete before API schema lock.
Integration Testing
Validate with Amazon sandbox, load test, security review, and schema confirmation.

## Slide 3
Current State of Readiness
Component | Status | Details
Certificate Database Application | 95% Complete | 40 items in final UAT retest cycle
REST API Endpoints | Built | /api/v1/certificates, search by ASIN, GS1 JSON-LD
API Authentication | Built | Partner API keys with rate limiting (200 req/hr)
Amazon Developer Guide | CP2 Complete | Reviewed by GCC; feedback incorporated
GS1 Data Schema (JSON-LD) | Built | JSON-LD format per GS1 Web Vocabulary standard
Search by Product ID (ASIN) | Built | GET /api/v1/certificates/search/productid?type=ASIN
Partner-Scoped Data Filtering | Built | API responses filtered by partner association
Integration Model: Amazon pulls certificate data from our API.
All API endpoints, authentication, data schema, and partner filtering are built and operational.
Remaining work is database stabilization (UAT), schema confirmation with Amazon, and integration testing.

## Slide 4
Option A — Aggressive Timeline (Amazon’s Requested Dates)
Phase | Milestone | Dates | Duration
Phase 1 | Database Stabilization & UAT Retest | Apr 15 — May 7 | 3 weeks
Phase 2 | API Schema Finalization & Lock | May 8 — May 31 | 3.5 weeks
★ | AMAZON MILESTONE 1 — May 31, 2026: Finalized API Endpoint & Data Schema |  | 
Phase 3 | Integration Testing with Amazon Sandbox | Jun 1 — Jul 15 | 6 weeks
Phase 4 | Final QA & Production Hardening | Jul 16 — Jul 31 | 2 weeks
★ | AMAZON MILESTONE 2 — July 31, 2026: API Technical Implementation & Testing Complete |  | 
Phase 5 | Automated Badging Go-Live | Aug 1 — Aug 31 | Rollout
★ | AMAZON MILESTONE 3 — August 2026: Automated Badging Live |  | 
Option A is achievable provided:
• GCC commits to completing UAT retest by May 7 with dedicated testing time
• No new feature requests are introduced during the stabilization phase
• All 5 pending discussion items are resolved by May 1
• Amazon sandbox credentials are available by June 1

## Slide 5
Option A — Phase Details
Phase 1: DB Stabilization (Apr 15 — May 7)
Deploy code fixes (24 files) + 4 SQL migration scripts Client UAT retest of 40+ resolved items Resolve retest failures Resolve 5 items pending client decision Data cleanup (test entries, hierarchy fixes) Exit Criteria: All critical/high QC items confirmed fixed
Phase 2: API Schema Lock (May 8 — May 31)
Confirm GS1 JSON-LD schema meets Amazon CPF requirements Document final field mappings (ASIN-only per Amazon) Lock API contract — no breaking changes after this date Publish final API documentation for Amazon Production deployment of stabilized database
Phase 3: Integration Testing (Jun 1 — Jul 15)
End-to-end testing with Amazon sandbox environment Validate Amazon can pull cert data via our API Verify ASIN search, GS1 format, partner filtering Load testing and performance validation Security review of API authentication
Phase 4: Final QA & Go-Live (Jul 16 — Aug 31)
Final QA pass with Amazon technical team Production hardening and monitoring setup Coordinate go-live with Amazon Monitor initial automated badge cycles Transition to steady-state operations

## Slide 6
Option B — Buffered Timeline (+1 Month, End of Q3 2026)
Phase | Milestone | Dates | Duration
Phase 1 | Database Stabilization & UAT Retest | Apr 15 — May 31 | 6 weeks
Phase 2 | API Schema Finalization & Lock | Jun 1 — Jun 30 | 4 weeks
★ | AMAZON MILESTONE 1 — June 30, 2026: Finalized API Endpoint & Data Schema |  | 
Phase 3 | Integration Testing with Amazon Sandbox | Jul 1 — Aug 15 | 6 weeks
Phase 4 | Final QA & Production Hardening | Aug 16 — Aug 31 | 2 weeks
★ | AMAZON MILESTONE 2 — August 31, 2026: API Technical Implementation & Testing Complete |  | 
Phase 5 | Automated Badging Go-Live | Sep 1 — Sep 30 | Rollout
★ | AMAZON MILESTONE 3 — September 2026: Automated Badging Live |  | 
Key Differences from Option A:
• +3 weeks UAT buffer — accounts for historically observed 15–30 new items per retest cycle
• +2 weeks schema review — allows iteration with Amazon technical team on CPF requirements
• Same testing time — integration testing (6 weeks) and final QA (2 weeks) unchanged
• End of Q3 alignment — completes within a natural reporting boundary

## Slide 7
Side-by-Side Comparison
Milestone | Option A (Aggressive) | Option B (Buffered) | Delta
API Schema Finalized | May 31, 2026 | June 30, 2026 | +1 month
API Implementation & Testing | July 31, 2026 | August 31, 2026 | +1 month
Automated Badging Go-Live | August 2026 | September 2026 | +1 month
UAT Stabilization Window | 3 weeks | 6 weeks | +3 weeks
Integration Testing Time | 6 weeks | 6 weeks | Same
New API Development Required | None | None | API is built
The API is fully built. No new development is required. The remaining effort is database stabilization, schema confirmation, and integration testing.

## Slide 8
Schedule Risk Factors
Risk | Impact | Likelihood | Mitigation
UAT retest generates significant new defects | Delays Phase 1; cascades to all milestones | Medium-High | Feature freeze after Phase 1. Only bug fixes, no new scope.
New feature requests during UAT | Scope creep delays stabilization | Medium | All new requests treated as formal Change Requests with separate timeline.
Amazon schema requirements change after review | Rework on finalized API contract | Medium | Early schema review with Amazon. Lock with formal sign-off.
Client availability for testing | UAT cycle extends beyond window | Medium | Detailed test cases provided. Set testing windows with committed dates.
Amazon sandbox access delays | Blocks integration testing | Low-Medium | Request sandbox credentials by May 15 regardless of timeline option.

## Slide 9
External Dependencies
The following items are outside of Anuki’s direct control and must be completed by the indicated parties.
Dependency | Owner | Needed By | Status
Complete UAT retest of 40 open items | GCC (Carly) | May 7 (A) / May 31 (B) | Not Started
Decisions on 5 pending discussion items | GCC (Carly / Dan) | May 1 | Pending
Amazon SP-API sandbox credentials | GCC / Amazon | Jun 1 | Not Requested
Amazon technical team schema review | Amazon | Jun 15 | Not Scheduled
Final production URL / DNS configuration | GCC | Jul 1 | Pending
Real certificate data loaded in production DB | GCC (Analysts) | Jul 1 | Partial
Schedule Impact: Any delay in the above dependencies directly impacts the Amazon milestone dates.
The UAT retest completion is the single largest dependency controlling the schedule.

## Slide 10
Recommendation
Anuki Recommends Option B (Buffered Timeline)
1. Historical pattern:
Every UAT cycle on this project has generated 15–30 new items. Option A assumes a clean retest, which has not occurred in any prior cycle.
2. API is already built:
No new API development is required. Amazon pulls data from our existing endpoints. The remaining work is stabilization and testing — not construction.
3. Accountability protection:
A missed aggressive deadline damages the Amazon relationship more than a met conservative one.
4. Q3 alignment:
Option B completes by end of Q3 2026, a natural reporting boundary.
However, if Amazon requires the aggressive timeline, Option A is achievable
provided GCC commits to completing UAT by May 7 with no new feature requests.

## Slide 11
Immediate Next Steps
Action | Owner | Due Date
Confirm timeline option with Amazon | GCC | April 15, 2026
Deploy current code fixes + SQL migration scripts | Anuki | April 16, 2026
Begin UAT retest using provided test cases (40 items) | GCC | April 17, 2026
Resolve 5 pending discussion items | GCC + Anuki | April 30, 2026
Request Amazon sandbox credentials | GCC | May 1, 2026
Complete UAT retest cycle | GCC | May 7 (A) / May 31 (B)
Questions or concerns? Contact Anuki Consulting to discuss timeline options. We are committed to delivering a high-quality, reliable integration for the Amazon partnership.

## Slide 12
Thank You
Anuki Consulting
Prepared for GreenCircle Certified — April 2026
CONFIDENTIAL