Revolutionizing Business Processes

Contract Prepared For:

GreenCircle Certified

Certified Database Proposal

Change Order

### Executive Summary

Through our collaborative discovery process, the GCC Database project has evolved significantly from its original scope, resulting in a more comprehensive and valuable solution for your organization. This change order documents the enhanced deliverables and adjusted timeline that have emerged from our iterative design process.

Project Evolution:

Enhanced Value: Transformed from basic interface to enterprise-grade system.

Timeline Adjustment: +23-29 weeks to accommodate comprehensive requirements.

Collaborative Discovery: Iterative stakeholder feedback process revealed additional business-critical needs.

### Scope Enhancement & Timeline Impact Summary

| Scope Enhancement | Timeline Impact | Priority Level | Business Value |
| --- | --- | --- | --- |
| Collaborative Requirements Discovery Process | +8 weeks | HIGH | Comprehensive stakeholder alignment |
| Front-End System Redesign | +4–5 weeks | HIGH | Enterprise-grade user experience |
| Stakeholder Design Refinement Process | +3–4 weeks | MEDIUM | Polished, user-tested interface |
| Product Management & Bulk Upload System | +2–3 weeks | HIGH | Operational efficiency & scalability |
| Enhanced Field Management System | +2 weeks | HIGH | Dynamic content management |
| Enhanced User Role System | +1–2 weeks | MEDIUM | Security & access control |
| Dashboard & Metrics System | +1–2 weeks | MEDIUM | Real-time business intelligence |
| Partner & Status Management Enhancements | +1–2 weeks | MEDIUM | Multi-partner workflow support |
| Advanced Search & Filtering | +1 week | MEDIUM | Enhanced user productivity |
| Amazon API Integration Enhancement | TBD | PENDING | Strategic partnership alignment |
| TOTAL IMPACT | +23–29 weeks | - | Comprehensive Enterprise Solution |

### Original Scope

Timeline: 14-18 weeks
Budget: $70,000

Primary Goal: Replace Ecomedes platform with basic database interface

Original Deliverables

Database expansion with enhanced fields

Basic front-end interface (simple replacement)

Amazon Climate Pledge Friendly API integration

Role-based user management

Certificate viewing and management

Internal testing and validation

Original Client Responsibilities

Complete requirements gathering and user stories (upfront)

Business Acceptance Testing (BAT/UAT)

Content review and approval

Go-live coordination

### Enhance Project Scope & Value Delivery

Through our collaborative discovery process, we've identified opportunities to deliver significantly enhanced value beyond the original project scope. These scope enhancements reflect a deeper understanding of your business needs and will result in a more comprehensive, enterprise-ready solution.

1. Collaborative Requirements Discovery Process

Timeline Impact: +8 weeks

Discovery Process Evolution: Our initial plan anticipated complete requirements documentation upfront. However, the collaborative discovery process revealed that the most effective approach was iterative requirements gathering, allowing for:

Deeper Understanding: Weekly stakeholder sessions uncovered business needs not evident in initial discussions

Stakeholder Alignment: Multiple department perspectives required integration and consensus-building

User Story Development: Anuki developed comprehensive user stories based on stakeholder input for validation and refinement

Process Benefits:

Enhanced understanding of business workflows

Better stakeholder buy-in through participatory design

More thorough requirement validation

Reduced risk of post-deployment change requests

2. Front-End System Redesign

Timeline Impact: +4-5 weeks | Scope Impact: HIGH

Original Scope: Basic interface to replace Ecomedes Expanded to Include:

60+ wireframe screens across 4 user roles

Advanced filtering and search with multi-level categories

Responsive design (desktop and mobile)

Role-based UI customization

Interactive dashboards with real-time metrics

Advanced forms with conditional field logic

Multi-select interfaces and bulk operations

Modern UX patterns and professional visual design

3. Enhanced Field Management System

Timeline Impact: +2 weeks | Scope Impact: HIGH

Added Requirements:

Certificate Field Management interface

Dynamic field addition capabilities

Inline editing for all certificate fields

CSF Attributes management system

Admin control over field visibility and requirements

4. Product Management & Bulk Upload System

Timeline Impact: +2-3 weeks | Scope Impact: HIGH

Original: Basic product association Expanded to Include:

Multi-format product identifier management (ASIN, UPC, GTIN, EAN)

Bulk upload capabilities (business critical requirement)

Individual columns for each identifier type

Multi-select deletion and status changes

Partner-specific product visibility

Import/export capabilities

Creation date and creator tracking

Business-Critical Enhancement: During requirements discovery, bulk upload capabilities were identified as essential for operational efficiency and moved from future-phase consideration to immediate implementation.

Note: This change demonstrates our responsive approach to emerging business needs during the collaborative design process.

5. Partner & Status Management Enhancements

Timeline Impact: +1-2 weeks | Scope Impact: MEDIUM

Added During Design Review:

Partner Field (Amazon/Wayfair) as required field with multi-select

Status Type Field for tracking non-proceeding clients

Multiple partner support requiring database restructuring

Company Contact Fields split (URL and Email separation)

6. Enhanced User Role System

Timeline Impact: +1-2 weeks | Scope Impact: MEDIUM

Original: Basic role-based access Enhanced to Include:

Four distinct user roles (Public, External, Analyst, Admin)

Granular field-level permissions

External user assignment based on tags/fields

Company-specific access control

Tag-based partner access

7. Dashboard & Metrics System

Timeline Impact: +1-2 weeks | Scope Impact: MEDIUM

New Requirements:

10+ specific dashboard metrics

Real-time certificate status tracking

Monthly creation/expiration reporting

Active certificate counts by various dimensions

Role-based dashboard access control

8. Advanced Search & Filtering

Timeline Impact: +1 week | Scope Impact: MEDIUM

Enhanced Features:

Flexible search with misspelling tolerance

Multi-level category filtering (3 levels deep)

Dynamic filter options based on active certificates

Advanced sorting capabilities

Mobile-responsive filter interfaces

9. Stakeholder Design Refinement Process

Timeline Impact: +3-4 weeks | Scope Impact: MEDIUM

- Collaborative Design Enhancement: Multiple stakeholder review cycles ensured the final design meets all user needs and business requirements:

Visual Optimization: Typography, alignment, and spacing refinements for better user experience.

Functional Enhancements: Additional filter options (APR, LEED) identified through user feedback.

Content Standardization: Category naming and formatting consistency improvements

Usability Improvements: Enhanced readability and intuitive navigation based on stakeholder testing.

Value Added: These iterative refinements ensure a polished, user-friendly interface that meets enterprise standards.

10. Amazon API Integration Enhancement

Timeline Impact: TBD | Scope Impact: TO BE DETERMINED

Collaborative Assessment: We're scheduling a joint session within 1-2 weeks to align additional field requirements requested by Amazon, ensuring optimal integration value for your certification program.

### Items Out of Scope

To manage scope, several items were documented as out-of-scope:

Notifications & Alerts System

Clone Feature Enhancements (selective field carry-over)

Product-Specific ASIN Fields (additional metadata)

Customized Reporting Widgets

Additional Third-Party API Integrations (beyond Amazon)

Note: Bulk Upload for Product Identifiers was initially listed as out-of-scope but was later confirmed as in-scope due to business requirements.

### Timeline Updates

### Milestones:

6/27 – Wireframes & Requirement complete

9/5 – Development Complete

9/19 – Testing Complete

10/3 – Go live

### Coordination:

9/8 – 9/19: Business Acceptance Testing, Defect Resolution

9/8 – 9/19: API Testing with Amazon

9/22 – 10/3: Deployment Activities

### Fees and Payment Terms

The total cost for the database project is $70,000. The payment will be structured as follows:

30% Upfront Payment: A payment of $21,000 is required upfront before the commencement of the project. This will cover the initial phases, including requirements gathering, analysis, and architectural design.

40% Midway Payment: An additional $28,000 will be due upon completion of the API development phase, ensuring that database and front-end structures are in place.

30% Upon Completion: The remaining $21,000 will be due upon successful project delivery and post-deployment validation.

Please note that the estimate provided does not include hosting fees, monitoring, or ongoing maintenance costs. These services can be arranged at an additional cost if required.

IN WITNESS WHEREOF, the parties hereto have executed this proposal as of the date last written below.

Acknowledgment

I hereby acknowledge that I have read, understood, and agree to the terms and conditions outlined in this proposal.

Approval

By signing this proposal, the client authorizes Anuki Consulting to proceed with the project as outlined and agrees to the payment terms specified.

Client Information

GreenCircle Certified, LLC

Name: Julie Golden
Title: Vice President of Marketing

Signature: __________________________

Date: __________________________

Consultant Information

ANUKI CONSULTING, LLC

Name: Shawn West
Title: Vice President

Signature: __________________________

Date: __________________________